## Burn down chart
| Sprints completed | Expected Story Points | Story Points
| 0 | 50 | 50
| 1 | 20 | 32
| 2 | 0 | 12
Sprint 1
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 33 | 33
19 | 31 | 31
18 | 28 | 28
17 | 26 | 28
16 | 24 | 28
15 | 22 | 26
14 | 21 | 25
13 | 20 | 23
12 | 19 | 19
11 | 18 | 18
10 | 17 | 17
9 | 16 | 17
8 | 14 | 17
7 | 12 | 16
6 | 10 | 14
5 | 8 | 14
4 | 6 | 12
3 | 4 | 11
2 | 2 | 10
1 | 1 | 9
0 | 0 | 9
Sprint 2
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 38 | 38
19 | 36 | 37
18 | 34 | 36
17 | 32 | 34
16 | 31 | 32
15 | 29 | 31
14 | 27 | 31
13 | 26 | 30
12 | 24 | 30
11 | 22 | 30
10 | 20 | 28
9 | 18 | 25
8 | 16 | 23
7 | 14 | 23
6 | 12 | 23
5 | 10 | 21
4 | 8 | 19
3 | 6 | 17
2 | 4 | 16
1 | 2 | 15
0 | 0 | 13

## Hours
Date | Git Issue # | Story # | Task # | Task | Assignee | Hours | Tasks Remaining
2016-10-19 | 92 | 5, 14 | 1 | Create an Enquiry page to enable users to send enquiries to the site administrator. | Jacob Marks | 1.25 | 48
2016-10-19 | 92 | 5, 14 | 3 | Verify story is complete (Acceptance test). | Jacob Marks | 0.25 | 47
2016-10-19 | 95 | 11 | 1 | Create a page visible to Admin Only that allows them to view student submitted feedback on individual teachers. | Jacob Marks | 1 | 46
2016-10-19 | 95 | 11 | 3 | Verify story is complete (acceptance test). | Jacob Marks | 0.5 | 45
2016-10-19 | 94 | 19 | 1 | Create a page visible to Students Only that allows them to submit feedback on individual teachers. | Jacob Marks | 1 | 44
2016-10-19 | 94 | 19 | 3 | Verify story is complete (acceptance test). | Jacob Marks | 0.5 | 43
2016-10-19 | 96 | 15 | 1 | Expand the database for teacher application | Daik Ichiyama | 0.25
2016-10-19 | 96 | 15 | 3 | Redirect user to a new page to confirm they have sent the application. | Daiki Ichiyama | 0.25
2016-10-19 | 96 | 15 | 2 | Create a page visible for non-users (not logged in) to submit an application including a number of set fields which will be stored in the database for easier reporting later. | Daiki Ichiyama | 0.5 | 42
2016-10-19 | 97 | 17 | 1 | Create a page for Admin only which enables them to view teacher applications. | Daiki Ichiyama | 0.25
2016-10-20 | 97 | 17 | 1 | Create a page for Admin only which enables them to view teacher applications. | Daiki Ichiyama | 0.5 | 41
2016-10-20 | 97 | 17 | 2 | Allow Admin to view individual applications or delete them. | Daiki Ichiyama | 0.25 | 40
2016-10-21 | 96 | 15 | 1 | Expand the database for teacher application | Daiki Ichiyama | 0.25 | 39
2016-10-21 | 96 | 15 | 3 | Redirect user to a new page to confirm they have sent the application. | Daiki Ichiyama | 0.25 | 38
2016-10-21 | 89 | 4 | 1 | Expand the database for Teacher Contact Detail Page | Daiki Ichiyama | 0.25
2016-10-21 | 89 | 4 | 2 | Allow teacher accounts to edit relevant contact detail | Daiki Ichiyama | 0.25
2016-10-21 | 89 | 4 | 4 | Create teacher index page for students to select and view | Daiki Ichiyama | 0.5
2016-10-21 | 98 | 10 | 1 | Comment uncommented code | Benjamin Saljooghi | 0.5 | 37
2016-10-22 | 100 | N/A | 2 | Write unit tests for Student Feedback. | Jacob Marks | 1.5 | 36
2016-10-22 | 99 | N/A | 1 | Apply content and styling for Report Production. | Benjamin Saljooghi | 2 | 35
2016-10-23 | 99 | N/A | 5 | Apply content and styling for Enquiry Page. | Benjamin Saljooghi | 0.5 | 34
2016-10-23 | 96 | 15 | 6 | Verify story is complete (Acceptance test). | Daiki Ichiyama | 0.25 | 33
2016-10-23 | 97 | 17 | 4 | Verify story is complete (Acceptance test). | Daiki Ichiyama | 0.25 | 32
2016-10-23 | 89 | 4 | 1 | Expand the database for Teacher Contact Detail Page | Daiki Ichiyama | 0.5 | 31
2016-10-23 | 89 | 4 | 2 | Allow teacher accounts to edit relevant contact detail | Daiki Ichiyama | 2 | 30
2016-10-23 | 89 | 4 | 3 | Create Profile page displaying each current teacher’s contact and teaching details. | Daiki Ichiyama | 1 | 29
2016-10-23 | 89 | 4 | 4 | Create teacher index page for students to select and view | Daiki Ichiyama | 0.5 | 28
2016-10-23 | 89 | 4 | 7 | Verify story is complete (acceptance test) | Daiki Ichiyama | 0.25 | 27
2016-10-23 | 100 | N/A | 1 | Write unit tests for Teacher Applications. | Jacob Marks | 2 | 26
2016-10-23 | 100 | N/A | 3 | Write unit tests for Teacher Contact Detail Page. | Jacob Marks | 1 | 25
2016-10-23 | 99 | N/A | 2 | Apply content and styling for Teacher Application. | Benjamin Saljooghi | 1 | 24
2016-10-23 | 99 | N/A | 6 | Apply content and styling for About Us page. | Benjamin Saljooghi | 0.5 | 23
2016-10-23 | 99 | N/A | 3 | Apply content and styling for Teacher Review. | Benjamin Saljooghi | 0.5 | 22
2016-10-23 | 90 | 23 | 1 | Create static About us page displaying general information about the school. | James Confessore | 0.5 | 20 | Jumped 2 here because this task was assigned twice
2016-10-23 | 91 | 24 | 1 | Create static location page with the address of the school and contact numbers and a map. | James Confessore | 1.5 | 19
2016-10-23 | 86 | N/A |  | Add Student Details Table, correctly referencing User table. | James Confessore | 1.5 | 18
2016-10-23 | 91 | 24 | 2 | Verify story is complete (acceptance test) | James Confessore | 0.5 | 17
2016-10-24 | 99 | N/A | N/A | Apply content and styling for Signup page, Contracts page, and Users page | Benjamin Saljooghi | 2 | 13 | Three tasks completed here (only 1 in this commit; other 2 are being added here retrospectively) but added 2 and removed 3 duplicate ones. Thus total count is "4" tasks completed. Therefore 17->13
2016-10-24 | 99 | N/A | 8 | Apply content and stlying for Home page. | Benjamin Saljooghi | 0.5 | 12
2016-10-25 | 93 | 28 | 2 | Acceptance testing for Student Lesson Booking | Benjamin Saljooghi | 0.5 | 11
2016-10-25 | - | - | - | Various Updates | James Confessore | 1.5