## Sheet1
Backlog Item | Estimate | Priority | MoSCoW | Notes
Link between gumtree advertisements and property management website. | 1 | 20 | Must | Property ID.
Images of listed properties. | 1 | 13 | Should | External hosting? Can a property owner upload their own images?
Uploading Images | 1 | 18 | Could
Current Tenant Lease Information | 2 | 19 | Could
Time slots for inspections - Creation. | 2 | 11 | Must | Logic statements for acceptance criteria on inspections.
Time slots for inspections - Booking. | 2 | 12 | Must | Logic statements for acceptance criteria on inspections.
Data validation on inspection requests to ensure legitimate requests are made. | 2 | 14 | Should | Email validation? Property management staff is only able to specify inspection times. Multiple tenants can inspect at one time. What is the limit for users able to register for an inspection?
Current tenant profile database entries and permissions. | 2 | 5 | Must
Prospective tenant profile database entries and permissions. | 2 | 6 | Must
Account creation. | 2 | 7 | Must
Email notifications. | 2 | 17 | Could
Watchlist feature. | 2 | 15 | Could
Waitlist feature. | 3 | 16 | Could
Login and identification. | 4 | 8 | Must | Plaintext?
Staff profile database entries and permissions. | 4 | 4 | Must
Property owner profile database entries and permissions. | 4 | 3 | Must
Property manager profile database entries and permissions. | 5 | 2 | Must
Filtered list view capabilities. | 8 | 9 | Must
Filtered search capabilities. | 8 | 10 | Must
User interface. | 8 | 1 | Must
Things to keep in mind:
Must, should and could have.
Consistency
Relativity
Fungibility
New Stories